## Sheet1
Street | Tree Location | Tree Species | Primary reason for tree being identified for replacement | Summary of ITP Advice | ITP Advice | Other Party Consulted | Streets Ahead Response | Streets Ahead Proposal | Final Decision | Decision Maker | Signature | Date Released
ALBERT ROAD | O/S 303/301 | Fraxinus excelsior | TR: Felling, network damage | Remove and replace tree. | Extensive damage to footway. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
ALBERT ROAD | O/S 305-307 | Acer pseudoplatanus | Substantial cavity @ 3m, and kerb damage | Retain Tree. | Small enclosed cavity, does not compromise integrity. | ITI | Not causing damage to highway | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
Barker's Road | opposite 33 | Acer pseudoplatanus | f/w mounded, cannot repair without unacceptable root damage, kerbstone absent | The two trees are in good condition. We advise that there is no arboricultural need to remove these trees. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these two trees. The tree opposite number 33 is causing significant damage to the pavement and damage to the kerb. The tree is leaning into the carriageway. We do not consider there to be engineering solutions which would resolve these problems. We advise that this tree should be removed and replaced. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Barker's Road | o/s 63 | Acer pseudoplatanus | Rooting above tarmac in f/w, will be damaged upon planing off | The two trees are in good condition. We advise that there is no arboricultural need to remove these trees. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these two trees. The tree outside number 63 is not causing significant damage. We consider that engineering solutions 2,3 and 7 would enable the retention of this tree. We advise the Council to consider this. | None Required | N/A | Unable to suggest removal in light of tree at opp 33 kerbed through . Kerb frontage to tree recommended and ramp over at footway | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
CHESTERFIELD ROAD SOUTH | CENTRAL RESERVATION, directly opposite 1-2 Ches Rd So | Fagus sylvatica | TR: Felling, decay | Retain Tree. | Tree in satisfactory condition. | ITI | ITI to inspect tree | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
CROMWELL STREET | o/s 11 | Prunus serrulata | Poor overall condition, surface roots damaging footway. (TR: Felling-) | Retain Tree. | Tree in satisfactory condition. No other reason to remove. | ITI | Recommend surface over footway | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 93 | Sorbus aucuparia sp | Extensive stem decay, very poor specimen | We advise that the Council should take steps to prevent this happening again. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 76 | Prunus Kanzan | Topped in past, stem wounding, poor specimen | We advise that the Council should take steps to prevent this happening again. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 110 | Sorbus aucuparia | decayed topping point into main stem | we advise that it would be prudent to remove and replace these trees. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 112 | Prunus Padus | basal/root decay | We therefore advise that the Council could reconsider the plan for these three trees. Further advice - 22/07/16: Since there do not appear to be other reasons requiring the removal and replacement of this tree, we advise that the Council should retain it, and subsequently monitor its condition. - | None Required | N/A | ITI verified disease continue with replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 114 | Sorbus aucuparia sp | Extensive Coriolus versicolor stem decay | we advise that it would be prudent to remove and replace these trees. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 118 | Prunus Kanzan | F/W mounded and cracked | advise that the Council would be justified in removing and replacing this tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 132 | Prunus Kanzan | Stem wounded and f/w cracked | we advise that it would be prudent to remove and replace these trees. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 24 | Prunus Kanzan | Extensive stem bark necrosis and f/w damage | we advise that it would be prudent to remove and replace these trees. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 57-59 | Prunus Kanzan | Stem split, poor specimen | We advise that the Council should take steps to prevent this happening again. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 83 | Prunus Kanzan | Previously topped and stem wounding at crown break, poor structural condition | We advise that the Council should take steps to prevent this happening again. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 58 | Prunus Kanzan | Extensive stem bark necrosis F/W cracking also | we advise that it would be prudent to remove and replace these trees. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 40 | Prunus Kanzan | F/W mounding by extensive lateral rooting | We therefore advise that the Council could reconsider the plan for these three trees. | None Required | N/A | Slight wall damage surface over / slight ramp | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 6 | Prunus Kanzan | F/W cracking by shallow rooting | We therefore advise that the Council could reconsider the plan for these three trees. | None Required | N/A | Surface over / slight ramp | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 17 | Prunus Kanzan | Extensive stem bark necrosis and f/w mounding | We advise that the Council should take steps to prevent this happening again. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 29 | Prunus Kanzan | Extensive stem bark necrosis | We advise that the Council should take steps to prevent this happening again. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 49 | Prunus Kanzan | Stem ripped out, poor structural condition | We advise that the Council should take steps to prevent this happening again. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 43-45 | Prunus Kanzan | Significant stem and scaffold decay | we advise that it would be prudent to remove and replace these trees. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 35-37 | Prunus Kanzan | Basal decay, structural integrity in doubt | We advise that the Council should take steps to prevent this happening again. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 92 | Sorbus aucuparia sp | Stem cavity, poor condition | We advise that the Council should take steps to prevent this happening again. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 34 | Prunus Kanzan | Weak union at crown break | we advise that it would be prudent to remove and replace these trees. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | o/s 26 | Not sent to ITP | Not sent to ITP | We noted that the tree outside number 26, that had not been referred to us, is significantly diseased or damaged. We advise that it would be prudent to remove and replace this tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 98-98a | Sorbus aucuparia sp | Significant stem decay and dieback of crown and scaffold | We advise that the Council should take steps to prevent this happening again. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 131 | Prunus Kanzan | Ganoderma sp. basal decay and stem wounding | we advise that it would be prudent to remove and replace these trees. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Furniss Avenue | O/S 12 | Prunus Kanzan | Extensive stem bark necrosis, poor specimen | We advise that the Council should take steps to prevent this happening again. | None Required | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | see map | Tilia cordata X mongolica | Tree missing on inspection. (TR: Felling-) | Tree already removed | None Required | N/A | Replace tree as planned | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road - see map | Tilia x europea | TR: Felling - Dead | Tree already removed | None Required | N/A | Replace tree as planned | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road - see map | Tilia x europea | TR: Felling - Structural Integrity | Retain Tree. | Impact wound. Healing. | N/A | Reinvestigate tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road - see map | Tilia x europea | TR: Felling - Structural Integrity | Remove and replace tree. | Tree in poor condition. | N/A | Replace tree as planned | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road - see map | Tilia x europea | Not sent to ITP | Remove and replace tree. | Tree in decline. Internal cavity. | N/A | Replace tree as planned | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road - see map | Salix caprea | TR: Felling - Structural Integrity | Remove and replace tree. | Self set tree adjacent to retaining wall. | N/A | Replace tree as planned | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road - see map | Tilia x europea | Not sent to ITP | Remove and replace tree. | Self set against retaining wall. | N/A | Replace tree as planned | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | Kerbs displaced by buttress roots immediately behind, cannot repair without root damage | Engineering Solutions. | Kerb displaced. | N/A | Engineering solutions employed | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | Kerbs displaced by buttress roots immediately behind, cannot repair without root damage | Retain Tree. | No damage visible. | N/A | Reinvestigate tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | Extensive surface rooting above tarmac, will be damaged upon reconstruction | Retain Tree. | Kerb satisfactory. Root in rough footway. | N/A | Reinvestigate tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | Extensive surface rooting above tarmac, will be damaged upon reconstruction | Retain Tree. | No damage visible. | N/A | Reinvestigate tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | Extensive surface rooting above tarmac, will be damaged upon reconstruction | Engineering Solutions. | Root displacing kerb. | N/A | Footway damaged. Make good track with planings: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | Kerbs displaced by buttress roots immediately behind, cannot repair without root damage | Engineering Solutions. | Kerb displaced. | N/A | Carriageway ramped. Existing kerb removed & tarmaced: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
Rivelin Valley Road | Rivelin Valley Road | Tilia x europea | Kerbs displaced by buttress roots immediately behind, cannot repair without root damage | Engineering Solutions. | Kerb displaced. Footway ramped. | N/A | Engineering solutions employed | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | Kerbs displaced by buttress roots immediately behind, cannot repair without root damage | Engineering Solutions. | Kerb displaced. Root in carriageway. | N/A | Kerb damaged & out. Root damaging carriageway. Footway root tracing: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | Kerbs displaced by buttress roots immediately behind, cannot repair without root damage | Engineering Solutions. | Kerb displaced. Root in carriageway. | N/A | Foot in carriageway, carriageway lifted: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road - see map, adjacent driveway for convent | Fraxinus excelsior | TR: Felling - Dead | Remove and replace tree. | Self set tree. Set back from road. | N/A | Replace tree as planned | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road - see map, adjacent Convent driveway | Fraxinus excelsior | TR: Felling - Dead | Remove and replace tree. | Self set tree. Set back from road. | N/A | Replace tree as planned | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road - see map, just beyond driveway to convent | Fraxinus excelsior | TR: Felling - Structural Integrity | Remove and replace tree. | Self set tree. Set back from road. | N/A | Replace tree as planned | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road - at end of driveway for convent | Fraxinus excelsior | TR: Felling - Structural Integrity | Remove and replace tree. | Self set tree. Set back from road. | N/A | Replace tree as planned | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | Kerbs displaced by buttress roots immediately behind, cannot repair without root damage | Engineering Solutions. | Kerb displaced. | N/A | Thin kerb & extend tree pit: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | Kerbs uplifted by buttress roots immediately behind, cannot repair without root damage | Engineering Solutions. | Kerb displaced. | N/A | Extend tree pit, trim kerb: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | Kerbs uplifted by buttress roots immediately behind, cannot repair without root damage | Engineering Solutions. | Kerb displaced. | N/A | Kerb displaced, footways ramped due to root tracing. Visibility issue also with junction: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | Kerbs uplifted by buttress roots immediately behind, cannot repair without root damage | Engineering Solutions. | Kerb displaced. | N/A | Engineering solutions employed | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | Kerbs displaced by buttress roots immediately behind, cannot repair without root damage | Engineering Solutions. | Kerb displaced. | N/A | Extend tree pit, trim kerb: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | dead - dying (TR: Felling-) | Retain Tree. | No visible issue. | N/A | Reinvestigate tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Next to pedestrian crossing from Walkley Bank Plantation | Tilia x europea | TR: Felling - Structural Integrity | Remove and replace tree. | Major cavity. Decay extending into heartwood. | N/A | Replace tree as planned | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | dead/dying. (TR: Felling-) | Remove and replace tree. | Carriageway damaged. | N/A | Replace tree as planned | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | 10m southward from lime opposite 43, i.e. next one in the avenue | Tilia x europea | Kerbs displaced by buttress roots immediately behind, cannot repair without root damage | Remove and replace tree. | Kerb displaced - significant. Carriageway damaged. | N/A | Replace tree as planned | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Opposite 43 | Tilia x europea | Kerbs displaced by buttress roots immediately behind, cannot repair without root damage | Remove and replace tree. | Kerb displaced - significant. Carriageway damaged. | N/A | Replace tree as planned | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road opposite 35-37 | Tilia x europea | Kerbs displaced by buttress roots immediately behind, cannot repair without root damage | Engineering Solutions. | Kerb displaced. Footway already ramped. | N/A | Root in carriageway, footway ramped with root tracing: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Opposite 31 | Tilia x europea | Kerb stone missing, cannot repair/reinstall without tree damage | Engineering Solutions. | Kerb displaced. Previous half width kerb. Footway cracked. | N/A | Root tracing in footway and causing trip issues. Ramping would cause backfall onto 3rd party property: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | O/s 29-31 | Tilia x europea | F/W uplifted by extensive buttress rooting immediately adjacent | Engineering Solutions. | Footway ramped. | N/A | Already ramped & cracked. Kerbs displaced. Damage to 3rd party wall: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | O/s 25-27 | Tilia x europea | significant basal cavity/buttress decay; other stem cavity - probable coalescent decay. | Reinvestigate. | Cavity at base to 1.5m. Healing well. | ITI | Reinvestigate tree | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | O/s 21-23 | Tilia x europea | Kerbs displaced by buttress rooting immediately behind, unable to repair without root damage | Engineering Solutions. | Kerb displaced. | N/A | Thin kerb shaped option. Footway to ramp & extend tree pit: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Facing/opp 19 | Tilia x europea | Kerbs displaced by buttress rooting immediately behind, unable to repair without root damage | Engineering Solutions. | Kerb displaced. Carriageway damaged. | N/A | Footway surface damaged slightly. Root in carriageway: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | Rivelin Valley Road | Tilia x europea | significant cavity (TR: Felling-) | Retain Tree. | Cavity. Structurally satisfactory. | N/A | Reinvestigate tree | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
RIVELIN VALLEY ROAD | O/s 11a | Tilia x europea | Significant scaffold limb cavity (TR: Felling-) | Retain Tree. | No visible issue. | N/A | Reinvestigate tree | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
SHEPPERSON ROAD | o/s 27 | Acer platanoides | TR: Felling, damage to network | Engineering Solutions. | Kerb displaced. Flagstone footway damaged. | N/A | Replace flag with bitmac leave kerb | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
SHEPPERSON ROAD | o/s 30 | Tilia x europea | TR: Felling - Roots severed, tree is now at risk of wind throw | Reinvestigate. | Investigate tree stability. If unstable remove and replace. Tree possibly unstable. | ITI | Any kerbing d fronting could make the tree more unstable Arbour to advise: No footway damage | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
SHEPPERSON ROAD | o/s 35 | Acer pseudoplatanus | TR: Felling - Roots severed on inspection. Die back of canopy due to root loss. Tree appears to be unstable. (Kerbstone has cracked under compression) | Reinvestigate. | Investigate tree stability. If unstable remove and replace. Tree possibly unstable. | ITI | Roots possibly tracing into gully any kerb removal could make tree more unstable: Arbour to advise | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
SHEPPERSON ROAD | Opp 37, (on corner/side of 34) | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | Footway mounded and very narrow. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
THORPE HOUSE ROAD | o/s 10 | Tilia x europea | TR: Felling - Kerb absent. Cannot install full profile kerb due to buttress | Engineering Solutions. | Kerb absent. | N/A | Leave kerb/ recent repairs carried out to carriageway | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
THORPE HOUSE ROAD | o/s 16 | Tilia x europea | TR: Felling - Kerbs displaced by buttress. Unable to reset. | Engineering Solutions. | Kerb displaced. | N/A | Bullnose in carriageway: Root damage severe in carriageway: Roots tracing to wall: Recommend replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
THORPE HOUSE ROAD | o/s81 | Sorbus aucuparia | TR: Felling - Poor condition. Extensive loss of vitality. Less than 5 years safe useful life expectancy. | Remove and replace tree. | Tree in poor condition. Crown dieback. Reduced vitality. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22