## Sheet1
Street | Tree Location | Tree Species | Primary reason for tree being identified for replacement | Summary of ITP Advice | ITP Advice | Other Party Consulted | Streets Ahead Response | Streets Ahead Proposal | Final Decision | Decision Maker | Signature | Date Released
CANNON HALL ROAD | o/s 60 | Acer pseudoplatanus | TR: Felling - Significant footway uplift - shallow roots will likely preclude acceptable re-construction of footway. Roots also visible at surface - high likelihood of being damaged during planing. | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
CANNON HALL ROAD | o/s 75 | Tilia x europea | TR: Felling - Significant kerb displacement. Limited scope to install full profile kerbs due to buttress roots. | Engineering Solutions. | Thinner Kerb, Larger Tree Pit | N/A | Kerb pushed out by 170mm relative to carriageway line. Ramping would cause backfall to property: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
CANNON HALL ROAD | o/s 35/37 | Acer pseudoplatanus | TR: Felling - No scope to install full profile kerbs due to buttress roots. | Retain Tree. | None Required | N/A | Thin kerb already pushed out from line this will continue as roots creep into carriageway: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
CANNON HALL ROAD | o/s 56 | Platanus x hispanica | TR: Felling - no scope to install full profile kerbs due to buttress roots. | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
CANNON HALL ROAD | o/s 4 | Tilia x europea | TR: Felling - Significant footway uplift - shallow roots will likely preclude acceptable re-construction of footway. | Engineering Solutions. | Filling Pavement, Larger Tree Pit, Trim Hedge | N/A | Longitudinal damage to footway by roots. Providing larger tree pit to rear is not possible. To temporarily Retain Tree ramp after removal of existing bitmac. | Retain Tree | Retain Tree | Paul Billington |  | 2017-05-23
FULTON ROAD | adj 126 | Sorbus aria | Basal decay fungi present (Ganoderma sp). Extensive dieback in centre of canopy. 1/3 of the crown dead. (TR: Felling-) | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
FULTON ROAD | o/s 1 | Alnus incana | Adventitious shoots from roots have damaged large area of footway. No sustainable repair possible without significant damage to tree roots. (LARGE AREA OF FOOTWAY WILL REQ EXPOSURE TO FULLY GRIND). (TR: Felling-) | Engineering Solutions. | Filling Pavement, Abandon Fway | N/A | Increase size of tree pit. Retain Tree subject to ongoing condition survey and monitoring of stem wound. | Retain Tree | Retain Tree | Paul Billington |  | 2017-05-23
HAWKSLEY AVENUE | o/s 33-35 | Acer platanoides | TR: Felling, damage to network | Engineering Solutions. | Filling Pavement, Larger Tree Pit | N/A | Ramping of footway will direct water towards House. Location of large utility cover also creates level issues: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
HAWKSLEY AVENUE | o/s 52 | Prunus serrulata | TR: Felling, decay | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
HAWKSLEY AVENUE | o/s 57-59 | Prunus serrulata | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
HAWKSLEY AVENUE | o/s 5-7 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
HAWKSLEY AVENUE | o/s 17 | Prunus serrulata | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
HOLLYTHORPE RISE | o/s 5 | Acer platanoides | TR: Felling - Kerb displaced by buttress. Unable to reset | Engineering Solutions. | Remove Limb | N/A | Minor roots tracing to property Recommend surface over footway: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-05-23
HOLLYTHORPE RISE | o/s 1 | Acer platanoides | TR: Felling - Damage to footway by shallow roots. Utility/Service cover displaced. | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
LEES HALL ROAD | o/s 19 | Acer pseudoplatanus | TR: Felling - Cannot install full profile kerb due to buttress | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
LEES HALL ROAD | o/s 27 | Acer platanoides | TR: Felling - Moderate dieback. Less than 5 years safe useful life expectancy. | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
LEES HALL ROAD | o/s 2 | Tilia x europea | TR: Felling - Cannot reinstall full profile kerb due to buttress. | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
LEES HALL ROAD | o/s 57 | Acer platanoides | TR: Felling - Footway damaged by shallow roots | Engineering Solutions. | Ramping | N/A | Ramp Footway: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-05-23
LEES HALL ROAD | o/s 5-7 | Tilia x europea | TR: Felling - Footway ramped by shallow roots. | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
LEES HALL ROAD | o/s 13 | Tilia x europea | TR: Felling - Kerb displaced by buttress roots. Unable to reset. | Engineering Solutions. | Reset Kerb | N/A | Roots exposed on either side of tree in footway and ramping not possible due to other thresholds: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
LEES HALL ROAD | o/s 53 | Acer platanoides | TR: Felling - Footway ramped by shallow surface roots | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
LEES HALL ROAD | o/s 8/10 | Tilia x europea | TR: Felling - Kerb displaced. Cannot install full profile kerb due to buttress. | Engineering Solutions. | Thinner Kerb | N/A | Roots under channel: roots under wall bowing occurring: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
LEES HALL ROAD | o/s 24 | Acer platanoides | TR: Felling - Footway ramped by shallow roots | Engineering Solutions. | Filling Pavement, Larger Tree Pit | N/A | Footway heaved. Heave in footway roots tracing to property: If ramp provided it will give backfall: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
LEES HALL ROAD | o/s 6 | Tilia x europea | TR: Felling - Kerb displaced by buttress. Unable to reset. | Retain Tree. | None Required | N/A | Drive and wall recently repaired by roots tracing under wall, channel and drive: will cause future damage: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
LEES HALL ROAD | o/s 63 | Acer platanoides | TR: Felling - Moderate dieback. Less than 5 years safe useful life expectancy. | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
LEES HALL ROAD | o/s 2 | Tilia x europea | TR: Felling - Kerb displaced by buttress. Unable to reset. | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MARLCLIFFE ROAD | o/s 191 | Prunus serrulata | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MARLCLIFFE ROAD | o/s 19, flat 1 | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Root Pruning, Larger Tree Pit | N/A | Root tracing across vehicle access and getting damaged already: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MARLCLIFFE ROAD | o/s 61 | Prunus Kanzan | TR: Felling, damage to network | Engineering Solutions. | Root Pruning, Larger Tree Pit | Independent Tree Inspector | ITI and ITP both identify numerous Ganoderma fruiting bodies on the tree. ITP recommend root pruning. ITI advises that “severing roots to achieve a solution would be damaging to tree physiology and stability” as such the ITP advice is not practicable in this instance. Recommend Replacement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MARLCLIFFE ROAD | OPP 16 | Acer pseudoplatanus | TR: Felling, damage to network | Engineering Solutions. | Thinner Kerb, Remove Kerb, Larger Tree Pit | N/A | Roots / buttress in channel unable to place kerb in line: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MARLCLIFFE ROAD | o/s 82 | Sorbus aucuparia | TR: Felling, Weak unions at crown break - included union. Structural Integrity | Retain Tree. | None Required | Independent Tree Inspector | ITI has verified stem injury, decay, structural weakness and third party property damage – Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | opp junc w/ cross park rd. | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | opp Taylor news | Fraxinus excelsior | Extensive kerbstone disturbance, unable to repair/work round without unacceptable levels of root damage | Engineering Solutions. | Thinner Kerb, Larger Tree Pit | N/A | Roots in carriageway with displaced kerb: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | o/s 59 | Tilia x europea | Extensive f/w and kerb damage | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | opp 111-113 | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Reset Kerb | N/A | Roots /buttress into and under carriageway: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | OPP 97/95 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | opp 87 | Tilia x europea | TR: Felling, network damage | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | O/S 135-137 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | O/S 131-133 | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Remove Kerb | N/A | Kerb missing already: Backfall to property if ramped: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | o/s 99/101 | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Remove Kerb, Larger Tree Pit | N/A | Roots in carriageway If ramped backfall to property: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | o/s 97/95 | Tilia x europea | TR: Felling, network damage | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | o/s 83 | Tilia x europea | TR: Felling, network damage | Engineering Solutions. | Ramping | N/A | Roots tracing into property: Ramping would cause backfall: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | o/s 77 | Tilia x europea | TR: Felling, network damage | Engineering Solutions. | Ramping | N/A | Ramp would suffice: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | o/s 73/71 | Tilia x europea | TR: Felling, network damage | Engineering Solutions. | Larger Tree Pit | N/A | Ramp with half kerb: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | o/s air accessories | Tilia x europea | TR: Felling, network damage | Engineering Solutions. | Root Pruning, Larger Tree Pit | N/A | Footway damaged. Severe damaging roots: Roots tracing to property and under channel: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | opp 75 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | o/s 23 | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Thinner Kerb, Larger Tree Pit | N/A | Severe root tracing up to number 19 and in carriageway channel. Could only be retained if roots removed, two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | o/s 17/15 | Tilia x europea | TR: Felling, network damage | Engineering Solutions. | Larger Tree Pit | N/A | Longitudinal root damage under footway. Could only be retained if roots removed, two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | o/s 9 | Platanus x hispanica | TR: Felling, damage to network | Engineering Solutions. | Thinner Kerb | N/A | Possible thinner kerb / ramping, however footway would require ramping and would cause backfall to property: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | opp 51/53 | Tilia x europea | Rooting between kerbs into c/w, extensive rooting in c/w | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MEERSBROOK PARK ROAD | opp 59 | Tilia x europea | Rooting into c/w, no kerbstone, extensive damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MILDEN ROAD | o/s 67 | Fraxinus excelsior | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MILDEN ROAD | o/s 60-62 | Fraxinus excelsior | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MILDEN ROAD | o/s 4 | Acer pseudoplatanus | TR: Felling, damage to network | Engineering Solutions. | Filling Pavement | N/A | Buttress in carriageway : roots tracing to property previous problems of roots in private drain: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MILDEN ROAD | o/s 49 | Fraxinus excelsior | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MILDEN ROAD | o/s 61 | Fraxinus excelsior | TR: Felling, damage to network | Engineering Solutions. | Thinner Kerb | N/A | Unable to bed a kerb due to shallow roots: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MILDEN ROAD | o/s 14-16 | Fraxinus excelsior | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MILDEN ROAD | o/s 64 | Fraxinus excelsior | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MILDEN ROAD | o/s 54 | Fraxinus excelsior | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MILDEN ROAD | Adj-side of 50 Vainor road. | Fraxinus excelsior | TR: Felling, damage to network | Engineering Solutions. | Thinner Kerb | N/A | Roots tracing to property. Could only be retained if roots removed, two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement and no scope to utilise half kerb. Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MILDEN ROAD | o/s 30-32 | Fraxinus excelsior | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MILDEN ROAD | Opp 2 | Fraxinus excelsior | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MILDEN ROAD | o/s 6 | Fraxinus excelsior | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MILDEN ROAD | adj 99a Langsett ave | Fraxinus excelsior | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MILDEN ROAD | Adj 40 Vainor road, (bottom side of 2 Milden rd.) | Fraxinus excelsior | TR: Felling, damage to network | Engineering Solutions. | Thinner Kerb, Remove Kerb, Root Pruning | N/A | Could only be retained if roots removed, in conjunction with half width kerb, two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement. If root can be pruned then half kerb proposed: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MILDEN ROAD | adj 99 Langsett ave | Fraxinus excelsior | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MONA ROAD | O/S 102 | Prunus Kanzan | TR: Felling - Footway ramped by shallow surface roots | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MONA ROAD | O/S 98 | Prunus Kanzan | TR: Felling - Flagstones lifted by shallow surface roots. Cannot reset. | Engineering Solutions. | Replace Flags with Tarmac | N/A | Replace flags near tree with bitmac, relay remainder: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-05-23
MONA ROAD | O/S 78 | Prunus Kanzan | TR: Felling - Footway and Flagstones Raised by shallow roots. Unable to reset | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
MONA ROAD | O/S 50 | Prunus Kanzan | Structural Integrity | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
WILLIS ROAD | o/s 44 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
WILLIS ROAD | o/s 29 | Acer pseudoplatanus | TR: Felling, damage to network | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
WILLIS ROAD | adj 267 rear of Middlewood road | Acer pseudoplatanus | Damage to retaining wall by direct root pressure. (TR: Felling-) | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
WILLIS ROAD | adj rear of 265 Middlewood road | Liquidambar styraciflua | TR: Felling, damage to network | Engineering Solutions. | Filling Pavement, Replace Flags with Tarmac | N/A | Extend tree pit and ramp with tarmac: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-05-23
Adelaide Road | o/s 19 'Oakmount' | Betula pendula | Substantial basal cavity, multiple unoccluded stem wounds, coalesced decay within stem | Remove and replace tree. | The tree outside number 19 “Oakmount” is significantly diseased and damaged, is leaning towards the neighbouring property and is at risk of failing. We advise that this tree should be removed and replaced. | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
Adelaide Road | o/s 39-41 | Acer pseudoplatanus | Rooting between kerbstones into c/w - will be unacceptably damaged upon planing off, suspected Cryptostroma corticale also | Reinvestigate. | The tree outside number 39-41 is healthy. We do not believe it can have cryptostroma corticale as this disease only occurs after a long period of drought. We advise that there is no arboricultural need to remove this tree. We have therefore considered whether there are engineering solutions that would prevent the need for the removal and replacement of this tree. We consider that the position of this tree and the option of retaining the existing arrangement of kerb stones between its roots would allow it to be retained. This would be consistent with the general character of the neighbourhood, and would not present a hazard to pedestrians or motorists. We therefore advise that this solution should be considered. | Independent Tree Inspector | Retain tree as engineering solutions have been successfully applied. Monitor for future removal as third party wall has previously been damaged; now repaired. Engineering Solutions Applied - Subject to ongoing monitoring | Retain Tree | Retain Tree | Paul Billington |  | 2017-05-23
Glentilt Road | OPPOSITE 1 | Fraxinus excelsior | Previously topped - poor structural condition, weakly attached regrowth on decaying topping points | Reinvestigate. | The trees opposite numbers 1 and 5, and outside number 20 have all been previously topped, and may be in a poor condition which would justify removal and replacement. However, ground level inspection could not verify this, and we therefore advise the Council to consider whether an aerial inspection could be undertaken to confirm the condition of the trees. If the trees are confirmed to be in a poor condition, we advise that they should be removed and replaced. | Independent Tree Inspector | Tree condition assessed by Independent Tree Consultant and found to be acceptable, temporary solution to remove kerb: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-05-23
Glentilt Road | OPPOSITE 5 | Fraxinus excelsior | Previously topped - poor structural condition, weakly attached regrowth on decaying topping points | Reinvestigate. | The trees opposite numbers 1 and 5, and outside number 20 have all been previously topped, and may be in a poor condition which would justify removal and replacement. However, ground level inspection could not verify this, and we therefore advise the Council to consider whether an aerial inspection could be undertaken to confirm the condition of the trees. If the trees are confirmed to be in a poor condition, we advise that they should be removed and replaced. | Independent Tree Inspector | ITI verified disease: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
Glentilt Road | O/S 20 | Fraxinus excelsior | Kerbs absent - cannot replace without root damage, previously topped - poor structural condition | Reinvestigate. | The trees opposite numbers 1 and 5, and outside number 20 have all been previously topped, and may be in a poor condition which would justify removal and replacement. However, ground level inspection could not verify this, and we therefore advise the Council to consider whether an aerial inspection could be undertaken to confirm the condition of the trees. If the trees are confirmed to be in a poor condition, we advise that they should be removed and replaced. | Independent Tree Inspector | Buttress on kerb line and damage to rear wall: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
Glentilt Road | O/S 24 | Sorbus intermedia | Kerbs pushed into c/w by buttress root pressing immediately on kerb rear - cannot realign | Remove and replace tree. | The remaining four trees are in good condition and have good life expectancy. We advise that there is no arboricultural need to remove these trees. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these trees. The tree outside 24 is causing significant damage to the pavement, kerb and carriageway, and may lead to damage to an adjacent gully. Further investigation by way of excavation would be required to determine whether this damage can be resolved. We advise that the Council could consider this, but recognise that the extent of the damage may lead the Council to proceed with removing and replacing this tree. | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
Glentilt Road | O/S 8 | Sorbus intermedia | Buttress roots growing within c/w - no kerbstones, would be extensively damaged upon road repair | Engineering Solutions. | The remaining four trees are in good condition and have good life expectancy. We advise that there is no arboricultural need to remove these trees. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these trees. The tree outside number 8 causing some damage to the kerb. We consider that engineering solutions 5 and 7 would enable this tree to be retained. We advise the Council to consider this. | N/A | Tree is causing damage to rear wall to property by roots undermining foundation: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
Glentilt Road | O/S 1 | Platanus x hispanica | Buttress roots growing within c/w - no kerbstones, would be extensively damaged upon road repair | Engineering Solutions. | The remaining four trees are in good condition and have good life expectancy. We advise that there is no arboricultural need to remove these trees. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these trees. The trees outside numbers 1 and 33 are causing some damage to the kerb. We consider that engineering solutions 1, 5 and 7 would enable these tree to be retained. We advise the Council to consider this. | N/A | Tree protruding to channel line and roots tracing towards wall: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
Glentilt Road | O/S 33 | Sorbus intermedia | Kerbs pushed into c/w by buttress root pressing immediately on kerb rear - cannot realign | Engineering Solutions. | The remaining four trees are in good condition and have good life expectancy. We advise that there is no arboricultural need to remove these trees. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these trees. The trees outside numbers 1 and 33 are causing some damage to the kerb. We consider that engineering solutions 1, 5 and 7 would enable these tree to be retained. We advise the Council to consider this. | N/A | Kerb lifted by roots. Also roots tracing to wall and possible gully near tree frontage. Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
ALDRED ROAD | O/S 25 | Sorbus aucuparia | v poor condition half dead | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
ALDRED ROAD | O/S 19 | Prunus Kanzan | TR: Felling - Kerbs and flagstones displaced by roots. Unable to reset. | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
ALDRED ROAD | O/S 35-37 | Prunus Kanzan | TR: Felling - Flagstones displaced by shallow roots. Unable to reset | Engineering Solutions. | Larger Tree Pit, Replace Flags with Tarmac | N/A | Replace flags with bitmac: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-05-23
COX PLACE | Between 2-4 | Acer rubrum 'Bowhall' | TR: Felling - Whole of upper canopy is dead. | Retain Tree. | None Required | Independent Tree Inspector | ITI verifies tree is dead: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
GLEBE ROAD | O/s 60 | Prunus serrula | TR: Felling - Kerb displaced, unable to reset | Engineering Solutions. | Thinner Kerb | N/A | Ramp footway with tarmac: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-05-23
GLEBE ROAD | O/s 69-71 | Prunus serrula | TR: Felling - Footway uplifted by shallow roots. Kerbs displaced, cannot reset due to roots. | Engineering Solutions. | Filling Pavement | N/A | Ramp footway with tarmac: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-05-23
GLEBE ROAD | O/s 36 | Prunus serrula | TR: Felling - Kerb displaced, unable to reset. Shallow roots lifting footway | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
GLEBE ROAD | outside 45 | Sorbus aucuparia | TR: Felling- Decay. | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
GLEBE ROAD | Opp 38 | Prunus serrula | root damage and stem decay. (TR: Felling-) | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
GLEBE ROAD | O/s 59-57 | Prunus serrula | Armillary infection. (TR: Felling-) | Reinvestigate. | Further investigation | Independent Tree Inspector | ITI identifies canker and decay and replace on condition grounds: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
GLEBE ROAD | O/s 55 | Sorbus aucuparia sp | TR: Felling- Meripilus infection. | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
GLEBE ROAD | O/s 49 | Prunus serrula | footpath damage and stem decay. (TR: Felling-) | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
GLEBE ROAD | o/s 47 | Prunus sp | TR: Felling - Poor condition. Decay at base. | Tree already removed. | None Required | N/A | Tree already removed | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
HARTLEY BROOK ROAD | o/s 69 | Acer sp | Senescent | Retain Tree. | None Required | Independent Tree Inspector | ITI recommends felling and replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
SPRING HILL ROAD | O/s 57 . Adj paved garden. | Acer pseudoplatanus | Kerb displaced by buttress root. Unable to reset. (TR: Felling-) | Engineering Solutions. | Thinner Kerb, Remove Kerb, Larger Tree Pit | N/A | Slight wall damage and roots in channel: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
SPRING HILL ROAD | Opp 94 Commonside | Tilia x europea | Kerb displaced by buttress root. Unable to reset. (TR: Felling-) | Engineering Solutions. | Thinner Kerb, Remove Kerb | N/A | Roots tracing to property and growth narrowing footway: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
SPRING HILL ROAD | Adj garden of 57. Jct Commonside | Acer pseudoplatanus | Moderate decline of canopy. Less than 5 years safe useful life expectancy. (TR: Felling-) | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
SPRING HILL ROAD | Opp 5 spring hill. On jct. | Acer pseudoplatanus | TR: Felling - Footway ramped by surface roots. | Engineering Solutions. | Filling Pavement | N/A | Discriminating footway by roots reducing width: If ramped it will be severely steep footway and BT box will have to be reset: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
SPRING HILL ROAD | Opp 36 | Acer pseudoplatanus | TR: Felling - Footway ramped by shallow surface roots. | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
SPRING HILL ROAD | Opp 26 | Acer pseudoplatanus | TR: Felling - Kerb displaced by buttress roots. Unable to reset. Stem obstructing carriageway | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
SPRING HILL ROAD | 2nd tree on road, on right if facing uphill | Acer pseudoplatanus | TR: Felling - Footway ramped by shallow surface roots. | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
SPRING HILL ROAD | O/s 49. Front of Left hand bay window | Acer pseudoplatanus | Kerb displaced by buttress root. Unable to reset. Footway becoming restricted by shallow surface roots. (TR: Felling-) | Remove and replace tree. | None Required | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
SPRING HILL ROAD | O/s 31 | Acer pseudoplatanus | TR: Felling - Rooting into carriageway | Retain Tree. | Consider exceptional circumstances. | N/A | Additional discrimination of footway damage to wall and roots in carriageway: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23
SPRING HILL ROAD | o/s 33 | Acer pseudoplatanus | TR: Felling - Kerb displaced by buttress roots. Unable to reset | Engineering Solutions. | Thinner Kerb, Remove Kerb | N/A | Roots tracing to wall evidence of previous repair roots in channel: Recommend Replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-05-23